## 🛡️ Risk Register
BLAISE KINGKO — GRC INTELLIGENCE & RISK REGISTER
Sources: CISA KEV ¦ US-CERT ¦ NIST NVD ¦ AWS/Azure Bulletins ¦ AI Governance Updates ¦ Frameworks: NIST CSF 2.0 ¦ ISO 27001 ¦ NIST 800-53 ¦ CIS Controls ¦ NIST AI RMF ¦ ISO 42001 ¦ EU AI Act ¦ Last Updated: 2026-05-29
RISK ID | DATE IDENTIFIED | SOURCE | CVE / ADVISORY ID | THREAT / VULN | THREAT CATEGORY | AFFECTED ASSET | AFFECTED SYSTEM | FRAMEWORK MAPPING | CONTROL FAMILY | LIKELIHOOD (1-5) | IMPACT (1-5) | RISK SCORE | RISK RATING | INHERENT RISK | CURRENT CONTROLS | RESIDUAL RISK | REMEDIATION | CIS CONTROL REF | OWNER | STATUS | DUE DATE | LAST UPDATED | NOTES
RR-001 | 2026-05-29 | CISA KEV | CVE-2024-21887 | Ivanti Connect Secure — Command Injection vulnerability actively exploited in the wild | IT — Network | VPN / Remote Access | Ivanti Connect Secure | NIST CSF 2.0: PR.PS-04, DE.CM-01 ¦ NIST 800-53: SI-2, RA-5 ¦ ISO 27001: A.12.6.1 ¦ CIS Control 7 | SI — System Integrity | 5 | 5 |  | Critical | Critical | Patch management process in place; WAF deployed | High | Apply vendor patch immediately; isolate affected systems pending patch | CIS Control 7.4 — Manage Operating System Vulnerabilities | Blaise Kingko | Open | 2026-06-04 | 2026-05-29 | Actively exploited per CISA KEV. Patch available. Escalate to CISO immediately.
RR-002 | 2026-05-29 | NIST NVD | CVE-2025-0282 | Ivanti Policy Secure — Stack-based buffer overflow enabling unauthenticated RCE | IT — Application | Policy Management Platform | Ivanti Policy Secure | NIST CSF 2.0: PR.PS-04, RS.MI-02 ¦ NIST 800-53: SI-3, SC-39 ¦ ISO 27001: A.14.2.2 ¦ CIS Control 2 | SC — System & Comms Protection | 4 | 5 |  | Critical | Critical | Network segmentation partially implemented | High | Emergency patch deployment; conduct IOC sweep; review authentication logs | CIS Control 2.2 — Ensure Software is Supported by Vendor | Blaise Kingko | Mitigating | 2026-06-07 | 2026-05-29 | RCE vector. Pre-auth. Requires immediate patch cycle bypass for emergency deployment.
RR-003 | 2026-05-29 | AWS Security Bulletin | AWS-2025-001 | AWS IAM confused deputy issue in cross-account role assumption — potential privilege escalation | Cloud — IAM | AWS Multi-Account Environment | AWS IAM / STS | NIST CSF 2.0: PR.AA-05 ¦ NIST 800-53: AC-6, AC-2 ¦ ISO 27001: A.9.2.3 ¦ CIS Control 5 | AC — Access Control | 3 | 4 |  | High | High | SCPs deployed; least-privilege IAM model in place across 500+ accounts | Medium | Audit all cross-account trust relationships; enforce ExternalId conditions on all assume-role policies | CIS Control 5.4 — Restrict Administrator Privileges | Blaise Kingko | Mitigating | 2026-06-14 | 2026-05-29 | Leverage existing IAM governance model. SCP guardrails reduce blast radius significantly.
RR-004 | 2026-05-29 | AI Governance Update | EU-AI-ACT-2025-HIGH-RISK | EU AI Act High-Risk AI System classification — internal LLM applications may require conformity assessment | AI/ML — Governance | Internal LLM Applications | GenAI Platform (AWS Bedrock) | NIST AI RMF: GOVERN 1.1, MAP 1.5 ¦ ISO 42001: 6.1.2 ¦ EU AI Act: Article 9, Annex III ¦ NIST 800-53: SA-11 | AI Risk Governance | 3 | 5 |  | High | High | AI Governance program active; NIST AI RMF framework implemented; prompt injection controls deployed | Medium | Conduct EU AI Act conformity assessment; document intended purpose and risk management system; prepare technical documentation per Article 11 | N/A — AI Governance Framework | Blaise Kingko | Open | 2026-07-01 | 2026-05-29 | Regulatory deadline risk. EU AI Act enforcement begins Aug 2026. High-risk classification triggers conformity assessment requirement.
RR-005 | 2026-05-29 | US-CERT | AA25-071A | CISA Advisory — SVR cyber actors targeting cloud environments via misconfigured service accounts | Cloud — Identity | Cloud Service Accounts | AWS / Azure Service Principals | NIST CSF 2.0: PR.AA-01, DE.AE-02 ¦ NIST 800-53: AC-6, AU-12 ¦ ISO 27001: A.9.4.4 ¦ CIS Control 4 | AC — Access Control | 4 | 4 |  | High | High | SIEM monitoring active; CloudTrail enabled; anomaly detection in place | Medium | Audit all service account permissions; rotate credentials; implement Just-In-Time access for privileged service accounts | CIS Control 4.7 — Manage Default Accounts | Blaise Kingko | Open | 2026-06-11 | 2026-05-29 | Nation-state TTPs. Aligns with existing SIEM architecture. Review CloudWatch anomaly alerts immediately.
RR-006 | 2026-06-08 | AWS Security Bulletin | 2026-030-AWS | Linux Kernel "Copy.fail"/"DirtyFrag" privilege-escalation family (CVE-2026-46300, CVE-2026-31431, CVE-2026-43284, CVE-2026-43500) — local LPE in espintcp/algif_aead/xfrm_user/esp modules affecting AWS self-managed compute | Cloud-Security | NIST CSF 2.0 PR.PS-02/DE.CM-09 ¦ NIST 800-53 SI-2/CM-2/CM-6/RA-5 ¦ ISO 27001 A.8.8/A.8.9 ¦ CIS Control 7/4 | SI-2, CM-6, RA-5 | 3 | 4 | 12 | High | High | AWS-managed control planes patched; customer self-managed compute (EKS/EC2/Bottlerocket) requires manual node rotation | Medium | Roll EKS-optimized AMIs and Bottlerocket hosts to patched builds (Bottlerocket >= v1.61.0); confirm Fargate platform versions >= 2026-06-09; validate via CSPM scan for zero non-compliant kernels | Control 7 (7.4) / Control 4 | Cloud Platform Engineering | Open | 2026-06-22 | 2026-06-15 | Shared-responsibility seam — AWS patches control plane only; full case bundle in Cloud-Security/2026-06-AWS-Bulletin-Linux-Kernel-CopyFail REVISED 2026-06-15 — AWS Fargate patches deployed all regions by June 15. Customer EKS/Bottlerocket/EC2 action still required; Likelihood reduced 4→3.
RR-007 | 2026-06-08 | Azure Security Update | CVE-2026-48567 | Azure HorizonDB Elevation of Privilege — authentication bypass by spoofing (CWE-290) in managed multi-tenant database control plane, CVSS 10.0 | Cloud-Security | NIST CSF 2.0 PR.AA-03/DE.CM-03/GV.SC-06 ¦ NIST 800-53 IA-2/AC-3/SC-7/CA-7 ¦ ISO 27001 A.5.15/A.8.5/A.5.23 ¦ CIS Control 6/13 | IA-2, AC-3, SC-7 | 3 | 5 | 15 | High | Critical | Microsoft platform-side patch pipeline (vendor-controlled); Entra ID conditional access as tenant-side compensating control | Low | Confirm Microsoft platform patch applied via Azure Service Health; audit HorizonDB auth logs 2026-05-28 to 2026-06-04 for spoofing indicators; enforce Entra ID-only authentication and Conditional Access MFA | Control 6 / Control 13 | Cloud Security Architecture | Open | 2026-06-15 | 2026-06-08 | Vendor-side CVSS 10.0 flaw — verification & IAM hardening case; full bundle in Cloud-Security/2026-06-MSRC-Azure-HorizonDB
RR-008 | 2026-06-08 | CISA KEV | CVE-2026-45247 | Mirasvit Full Page Cache Warmer (Magento/Adobe Commerce) — deserialization of untrusted data / PHP object injection enabling unauthenticated RCE, CVSS 9.8, actively exploited in the wild | Cloud-Security | NIST CSF 2.0 PR.PS-02/DE.CM-01/RS.AN-03 ¦ NIST 800-53 SI-2/SI-3/SI-10/IR-4 ¦ ISO 27001 A.8.8/A.8.28/A.8.16 ¦ CIS Control 16/7/17 ¦ PCI-DSS v4.0 Req 6.3.3/11.3 | SI-2, SI-3, SI-10 | 5 | 5 | 25 | Critical | Critical | WAF signatures (Imperva) available as interim compensating control; PCI-mandated file-integrity monitoring may detect web-shell drops | Low | Update Mirasvit Full Page Cache Warmer to v1.11.12+ on all Magento 2/Adobe Commerce instances immediately (target 2026-06-10); conduct web-shell forensic sweep of pub/media, var/, app/code directories; engage PCI Forensic Investigator if IOCs found | Control 16 (16.13) / Control 7 | Application Security / E-commerce Engineering | Open — Expedited | 2026-06-10 | 2026-06-08 | CISA federal due date 2026-06-06; active exploitation confirmed by Sansec/Imperva/SecurityWeek; full bundle in Cloud-Security/2026-06-CISA-KEV-Magento-Mirasvit
RR-009 | 2026-06-08 | AI Governance Update | Draft Guidelines — High-Risk AI Classification (Consultation closes 2026-06-23) | European Commission draft guidance on classifying AI systems as "high-risk" under EU AI Act Annex III; enforcement infrastructure being stood up; high-risk obligation deadlines extended to Dec 2027 / Aug 2028 | AI-Governance | NIST AI RMF GOVERN/MAP (1.1, 5.1) ¦ ISO 42001 Clauses 6.1.2/8.4/4.1 ¦ EU AI Act Article 6/Annex III ¦ GDPR Article 35 (DPIA overlap) | GOVERN, MAP | 3 | 3 | 9 | Medium | Medium-High | Existing ISO 42001 risk-assessment processes (where implemented) and NIST AI RMF MAP practices provide a transferable methodology for classification | Low | Compile complete AI-system inventory mapped to EU-resident exposure; classify each system against draft Annex III criteria using ISO 42001 Clause 8.4 template; consider submitting consultation feedback before 2026-06-23; build combined NIST AI RMF/ISO 42001/EU AI Act/GDPR evidence template | N/A — Regulatory/Governance | AI Governance Lead | Open — Proactive | 2026-09-08 | 2026-06-08 | 18-month runway to Dec 2027 milestone; full bundle in AI-Governance/2026-06-EU-AI-Act-HighRisk-Classification
RR-010 | 2026-06-08 | CISA KEV | CVE-2025-48595 | Android Framework integer overflow (CWE-190) enabling local elevation of privilege; CVSS 8.4; Google confirms limited, targeted exploitation (spyware/nation-state pattern); affects Android 14/15/16/16-QPR2 | IT-OT-Threats | NIST CSF 2.0 PR.PS-02/DE.CM-09 ¦ NIST 800-53 SI-2/CM-6 ¦ ISO 27001 A.8.8 ¦ CIS Control 4 (Mobile/BYOD) | SI-2, CM-6 | 4 | 3 | 12 | High | Medium | MDM/UEM enforcement of OS patch-level baselines on managed devices; app-vetting controls limiting locally-installed untrusted apps | Low | Push June 2026 Android security patch level to all managed/BYOD devices via MDM/UEM within 7 days; flag any device failing to report patched build for conditional-access restriction | Control 4 | Endpoint / Mobility Engineering | Open | 2026-06-15 | 2026-06-08 | Register entry only — mobile/endpoint scope did not meet full-bundle threshold (no direct AWS/IAM/CSPM/AI-platform nexus); monitor for KEV escalation
RR-011 | 2026-06-15 | CISA KEV | CVE-2026-35273 | Oracle PeopleSoft Enterprise PeopleTools (EMHub) — Missing authentication for critical function enabling unauthenticated RCE; CVSS 9.8; zero-day exploited by UNC6240 (ShinyHunters) May 27–June 9, 2026; active extortion campaign | IT-OT-Threats / Financial-Services | ERP Platform (HR, Finance, Student Administration) | Oracle PeopleSoft PeopleTools 8.61 / 8.62 | NIST CSF 2.0: PR.PS-04/DE.CM-01/RS.AN-03/RS.MI-02 ¦ NIST 800-53: SI-2/IA-2/AC-3/SI-10/IR-4/AU-6 ¦ ISO 27001: A.8.8/A.5.15/A.8.5/A.5.26 ¦ CIS Control 7/12/17 | SI-2, IA-2, AC-3, IR-4 | 5 | 5 | 25 | Critical | Critical | Network perimeter firewall; SIEM monitoring; vulnerability scanning (signatures not available during zero-day window) | Critical (without patch); High with VPN-only access compensating control | Apply Oracle emergency patch for CVE-2026-35273 to all PeopleTools 8.61/8.62 by June 22; restrict internet-facing PeopleSoft portals to VPN/internal access immediately; conduct threat hunt for UNC6240 IOCs from Mandiant June 11 report; engage IR retainer if IOCs found; assess SEC 4-day disclosure obligation if breach confirmed | CIS Control 7.4 / CIS Control 17.4 / CIS Control 12.2 | Enterprise Application Engineering / GRC | Open — Emergency | 2026-06-22 | 2026-06-15 | CISA KEV added 2026-06-12; federal due date 2026-07-03 (BOD 26-04); zero-day exploited by ShinyHunters (UNC6240) extortion campaign; Oracle out-of-band patch available June 12; full bundle in IT-OT-Threats/2026-06-CISA-KEV-Oracle-PeopleSoft
RR-012 | 2026-06-15 | MSRC | CVE-2026-45657 | Windows Kernel use-after-free RCE — wormable; CVSS 9.8; unauthenticated network attack, no user interaction; SYSTEM-level code execution; self-propagating exploit profile comparable to EternalBlue/WannaCry (June 2026 Patch Tuesday) | Cloud-Security / IT-OT-Threats | Windows Endpoints / Servers / Azure IaaS VMs / AWS EC2 Windows | Windows 10, Windows 11, Windows Server 2019/2022/2025 (all supported versions) | NIST CSF 2.0: PR.PS-04/PR.IR-01/DE.CM-09/RC.RP-01 ¦ NIST 800-53: SI-2/CM-6/SC-7/CP-9/RA-5 ¦ ISO 27001: A.8.8/A.8.9/A.8.22/A.8.13 ¦ CIS Control 7/4/11/12 | SI-2, CM-6, SC-7, CP-9 | 4 | 5 | 20 | Critical | Critical | Endpoint patch management (WSUS/Intune/SSM); network segmentation (NSGs/SGs/VPC); EDR (CrowdStrike/Defender); SMB east-west blocking partially implemented | High (without full patch deployment); Low after patch complete | Deploy June 2026 Windows cumulative update to ALL endpoints and servers within 72 hours (by June 18); prioritize internet-facing, DCs, and cloud VMs; block SMB (TCP 445) between network segments immediately as worm containment control; verify immutable backups exist before possible exploitation; use Azure Update Manager / AWS SSM Patch Manager for cloud VM compliance | CIS Control 7.4 / CIS Control 12.2 / CIS Control 11.2 | Cloud Platform Engineering / Endpoint Engineering | Open — Emergency | 2026-06-18 | 2026-06-15 | No confirmed exploitation at disclosure; wormable profile = treat as imminent (ZDI EternalBlue comparison); June 2026 Patch Tuesday (198 CVEs, largest ever); full bundle in Cloud-Security/2026-06-MSRC-PatchTuesday-WormableKernel
RR-013 | 2026-06-15 | MSRC | CVE-2026-47291 | Windows HTTP Protocol Stack (HTTP.sys) integer overflow/heap overflow RCE; CVSS 9.8; unauthenticated; single malicious HTTP packet achieves full server RCE; configurable registry mitigation available (MaxRequestBytes ≤ 65534) (June 2026 Patch Tuesday) | Cloud-Security / IT-OT-Threats | Internet-facing Windows Web Servers / Azure IaaS IIS / Cloud-hosted Web Infrastructure | Windows HTTP.sys (all IIS/HTTP.sys-exposed Windows Server versions) | NIST CSF 2.0: PR.PS-04/PR.PS-02/DE.CM-09 ¦ NIST 800-53: SI-2/CM-6/SC-5/SC-7 ¦ ISO 27001: A.8.8/A.8.9 ¦ CIS Control 7/4/12 | SI-2, CM-6, SC-7 | 4 | 5 | 20 | Critical | Critical | WAF; NSG inbound HTTP restrictions; endpoint patch management | Medium (with MaxRequestBytes registry workaround); Low after June 2026 patch applied | IMMEDIATE: Set MaxRequestBytes registry value ≤ 65534 (default 16384) on all IIS/HTTP.sys servers via GPO/SSM — eliminates exposure without reboot. Then: apply June 2026 cumulative update to all internet-facing Windows web servers by June 16. Remove registry workaround after patch confirmed installed. | CIS Control 7.4 / CIS Control 4.1 | Cloud Platform Engineering / Windows Sysadmin | Open — Emergency | 2026-06-16 | 2026-06-15 | Registry compensating control available immediately (no reboot required); full bundle in Cloud-Security/2026-06-MSRC-PatchTuesday-WormableKernel (combined with RR-012)
RR-014 | 2026-06-15 | CISA KEV | CVE-2026-7473 | Arista Networks EOS incomplete comparison vulnerability — processes non-configured tunnel traffic, bypassing tunnel policy enforcement; CVSS 6.9; actively exploited; NO VENDOR PATCH PLANNED | IT-OT-Threats | Enterprise Network Infrastructure / WAN / Data Center Switching | Arista EOS (all affected versions with tunnel configurations) | NIST CSF 2.0: PR.IR-01/DE.CM-01/GV.RM-06 ¦ NIST 800-53: SC-7/AC-4/SI-4/RA-3 ¦ ISO 27001: A.8.22/A.8.16/A.8.9 ¦ CIS Control 12/13 ¦ IEC 62443 Zone/Conduit model | SC-7, AC-4, SI-4 | 4 | 4 | 16 | High | High | Network firewall; SIEM monitoring; existing tunnel configurations as intended (but now unreliable as security boundary) | Medium (with interface ACLs, NetFlow monitoring, and defense-in-depth inline firewall at critical boundaries) | No patch available (vendor will not fix). Compensating controls: (1) Deploy explicit interface-level ACLs denying unexpected tunnel sources on all Arista EOS devices; (2) Enable NetFlow/sFlow telemetry on all affected devices with SIEM alerting for unexpected tunnel traffic; (3) For critical boundaries (OT/financial): deploy inline stateful firewall as defense-in-depth; (4) Execute formal risk acceptance with CISO/CRO sign-off by June 30. | CIS Control 12.2 / CIS Control 13.6 | Network Engineering / GRC | Open — Compensating Controls / Risk Acceptance | 2026-06-30 | 2026-06-15 | CISA KEV added 2026-06-09; BOD 26-04 due date June 30; Arista confirmed no patch planned; permanent unpatched state requires formal risk acceptance; IEC 62443 zone integrity implications for OT environments; full bundle in IT-OT-Threats/2026-06-CISA-KEV-Arista-EOS
RR-015 | 2026-06-15 | CISA KEV | CVE-2026-11645 | Google Chromium V8 out-of-bounds read/write enabling sandbox escape and arbitrary code execution via crafted HTML page; CVSS 8.8; actively exploited via phishing/malvertising; also affects all Electron-based enterprise desktop apps (VS Code, Slack, etc.) | IT-OT-Threats | Enterprise Endpoints / User Workstations / Cloud Console Users | Google Chrome, Microsoft Edge (Chromium), all Electron-based enterprise applications | NIST CSF 2.0: PR.PS-04/DE.CM-04/PR.AT-01 ¦ NIST 800-53: SI-2/SI-3/SC-18/AT-2 ¦ ISO 27001: A.8.8/A.8.7/A.6.3/A.8.23 ¦ CIS Control 7/9/14 | SI-2, SI-3, SC-18 | 5 | 4 | 20 | Critical | Critical | Chrome auto-update (if not blocked); MDM/Intune browser policy; web content filtering; EDR endpoint protection; email security (DMARC/DKIM) | Medium (Chrome/Edge patched); pending Electron app inventory and vendor patch assessment | Force Chrome and Edge update to latest stable via MDM/Intune — verify 100% compliance. Inventory all Electron-based enterprise apps and track embedded Chromium version for each. Push available Electron app updates; restrict unpatched Electron apps pending vendor fix. Update web filtering threat intel feeds. Send security awareness communication re: phishing/malvertising campaign. | CIS Control 7.4 / CIS Control 9.2 / CIS Control 14.1 | Endpoint Engineering / SOC | Open — Emergency | 2026-06-18 | 2026-06-15 | CISA KEV added 2026-06-09; BOD 26-04 due date June 30; key risk: Electron app coverage gap — Chrome auto-update alone insufficient; exploit is silent (no user prompt); session theft from cloud console workers is highest-probability impact; full bundle in IT-OT-Threats/2026-06-CISA-KEV-Chrome-V8
RR-016 | 2026-06-15 | CISA KEV | CVE-2026-20245 | Cisco Catalyst SD-WAN Manager (vManage) authenticated local OS command injection enabling arbitrary command execution as root via crafted file; CVSS 7.8; actively exploited; root on SD-WAN Manager = control of entire enterprise WAN fabric | IT-OT-Threats | Enterprise WAN Infrastructure / Network Management Plane | Cisco Catalyst SD-WAN Manager (vManage) | NIST CSF 2.0: PR.AA-05/PR.PS-04/DE.CM-03 ¦ NIST 800-53: SI-2/AC-6/AC-2/CM-3/AU-9 ¦ ISO 27001: A.8.8/A.5.15/A.8.22/A.8.32 ¦ CIS Control 5/7/8/12 | SI-2, AC-6, AC-2, CM-3 | 4 | 5 | 20 | Critical | Critical | RBAC on vManage; network-level restriction (variable); audit logging; MFA (variable by org) | High until patched; Medium with MFA + management-segment restriction + audit alerting | Apply Cisco security patch for CVE-2026-20245 immediately (target June 18). Simultaneously: audit all vManage accounts — remove inactive/shared accounts; enforce MFA on all admin accounts; restrict vManage to dedicated management network segment (no direct internet access); forward vManage audit logs to SIEM with alert on policy changes and file uploads; review logs from June 1–15 for exploitation indicators. | CIS Control 5.4 / CIS Control 7.4 / CIS Control 8.2 | Network Engineering / IAM | Open — Emergency | 2026-06-30 | 2026-06-15 | CISA KEV added 2026-06-09; BOD 26-04 due date June 30; authentication prerequisite (insider/compromised account); root on vManage = WAN-wide control; complementary PAM hardening critical; full bundle in IT-OT-Threats/2026-06-CISA-KEV-Cisco-SDWAN

## 📊 Risk Dashboard
GRC INTELLIGENCE DASHBOARD — BLAISE KINGKO
RISK SUMMARY | RISKS BY SOURCE
Total Risks Identified | CISA KEV
Critical Risks | NIST NVD
High Risks | US-CERT
Medium Risks | AWS Security Bulletin
Low Risks | Azure Security Update
Open Risks | AI Governance Update
Mitigating | NIST Framework Update
Closed This Period | ISO Update
AI/ML Risks | Internal Assessment
Cloud Risks
OT/ICS Risks
Past Due (Overdue)
FRAMEWORK COVERAGE
NIST CSF 2.0
NIST 800-53
ISO 27001
CIS Controls
NIST AI RMF
ISO 42001
EU AI Act

## 🔥 Risk Heat Map
RISK HEAT MAP — LIKELIHOOD vs IMPACT
LIKELIHOOD ↓ | IMPACT →
| 1 — Minimal | 2 — Minor | 3 — Moderate | 4 — Major | 5 — Catastrophic | LEGEND
5 — Almost Certain | 5 Medium | 10 High | 15 Critical | 20 Critical | 25 Critical | Critical (Score 20-25)
4 — Likely | 4 Low | 8 Medium | 12 High | 16 Critical | 20 Critical | High (Score 10-19)
3 — Possible | 3 Low | 6 Medium | 9 Medium | 12 High | 15 Critical | Medium (Score 5-9)
2 — Unlikely | 2 Low | 4 Low | 6 Medium | 8 Medium | 10 High | Low (Score 1-4)
1 — Rare | 1 Low | 2 Low | 3 Low | 4 Low | 5 Medium

## 📡 Intel Sources
INTELLIGENCE MONITORING SOURCES — BLAISE KINGKO GRC PROGRAM
SOURCE | URL / FEED | CATEGORY | FREQUENCY | FRAMEWORK RELEVANCE
CISA KEV | https://www.cisa.gov/known-exploited-vulnerabilities-catalog | Threat Intel | Daily | NIST CSF: DE.CM ¦ NIST 800-53: RA-5, SI-2
CISA Advisories | https://www.cisa.gov/news-events/cybersecurity-advisories | Threat Intel | Weekly | NIST CSF: DE.AE ¦ NIST 800-53: IR-4, SI-5
US-CERT Alerts | https://www.cisa.gov/uscert/ncas/alerts | Threat Intel | Weekly | NIST CSF: RS.CO ¦ NIST 800-53: IR-6
NIST NVD | https://nvd.nist.gov/vuln/search | Vulnerability | Weekly | NIST 800-53: RA-5 ¦ CIS Control 7
NIST 800-53 Updates | https://csrc.nist.gov/publications/detail/sp/800-53/rev-5/final | Framework | Quarterly | NIST 800-53 all control families
NIST CSF 2.0 Updates | https://www.nist.gov/cyberframework | Framework | Quarterly | NIST CSF 2.0 all functions
NIST AI RMF Updates | https://www.nist.gov/artificial-intelligence | AI Governance | Monthly | NIST AI RMF: GOVERN, MAP, MEASURE, MANAGE
ISO 27001 Updates | https://www.iso.org/standard/27001 | Framework | Annual | ISO 27001 all clauses and Annex A
ISO 42001 Updates | https://www.iso.org/standard/81230.html | AI Governance | Annual | ISO 42001 all clauses
EU AI Act | https://artificialintelligenceact.eu | AI Governance / Regulatory | Monthly | EU AI Act Articles 9, 10, 11, 13, 17
AWS Security Bulletins | https://aws.amazon.com/security/security-bulletins/ | Cloud Security | Weekly | NIST 800-53: SI-2 ¦ CIS Control 7 ¦ CSF: PR.PS
Azure Security Updates | https://msrc.microsoft.com/update-guide/ | Cloud Security | Weekly | NIST 800-53: SI-2 ¦ CIS Control 7 ¦ CSF: PR.PS
CIS Benchmarks | https://www.cisecurity.org/cis-benchmarks | Hardening | Quarterly | CIS Controls 1-18 ¦ NIST 800-53: CM-6
MITRE ATT&CK | https://attack.mitre.org | Threat Intel | Monthly | NIST CSF: DE.AE ¦ NIST 800-53: RA-3
MITRE ATLAS (AI) | https://atlas.mitre.org | AI Threat Intel | Monthly | NIST AI RMF: MAP 5 ¦ ISO 42001: 6.1.2